NXT SCHOOL · DESIGN BRIEF · BATCH 4 OF 4

Batch 4 — for Weeks 4–5 (26 Oct – 8 Nov)

Last call before 9 Nov, the Open Day recap, real-photo versions of the best ads and two more Reels.

| # | Deliverable | Format | Due |
| --- | --- | --- | --- |
| B4-1 | R6 · Last call | STATIC 4:5 + 9:16 | Mon 26 Oct |
| B4-2 | R7 · Open Day recap | PHOTO-BASED 4:5 + 9:16 | ~Tue 27 Oct |
| B4-3 | Top 2 ads · real-photo versions | PHOTO-BASED 4:5 + 9:16 | Wed 28 Oct |
| B4-4 | Reels · Kids Explain + scroll → create | VIDEO 9:16 (with Igor) | Wed 28 Oct |

RULES FOR EVERY BATCH Brand: Manrope ExtraBold headlines · navy #0F172A · light #F8FAFC · blue #007BFF → purple #7A5CFF gradient as accent only · ≥ 40% whitespace · final NXT logo file (the mockups use a placeholder wordmark). Sizes: feed 4:5 = 1080 × 1350 (≥ 60 px margins) + story 9:16 = 1080 × 1920 (keep top 250 px and bottom 380 px free of text and CTA). Re-layout for 9:16 — never just crop. CTA: one pill, "Prijavi dete →" (Open Day ads: "Prijavi se →"). Answers on phone-size text: min ~24 px at 1080 width. Facts = the website: regular 7.200 RSD · Open Day ponedeljak, 26. oktobar, 18–20 h · no "besplatno" until confirmed · level copy + "6 oblasti" as on the site. Never: AI-generated children’s faces · rows of kids staring at screens · "Demo Day" (it’s NXT Showcase) · seat counts (the site’s "Broj mesta je ograničen" is fine). Real child photos need signed parental consent. Delivery: PNG, named AdID_Creative_v#_ratio (e.g. P2_C3_LessScrolling_v1_9x16.png) → shared folder → Mladen signs off → Filip uploads.

| B4-1 R6 · Last call "Počinjemo 9. novembra" Retargeting · 27 Oct → 8 Nov |  |
| --- | --- |
| INSPIRATION Mockup R6 (4:5) | FINALIZE MOCKUP STATIC · 4:5 + 9:16 Due: Mon 26 Oct UPDATED 6 OCT (website) · regular price 7.200 · tick 2 = "Grupe kreću zajedno — 9. novembra" · goes live Tue 27 Oct (after the Open Day). Job: close warm parents before the program starts. Make / improve: • Same look as C5 (gradient), the date is the hero. • Price card + 3 ticks. • 4:5 + 9:16. On the image (exact text): — badge: POSLE OPEN DAY-A · POSLEDNJI POZIV — headline: Prva generacija počinje 9. novembra. — price: FOUNDING CENA 5.900 RSD mesečno · regularna 7.200 RSD — ticks: 4 nivoa, 1–8. razred · Grupe kreću zajedno — 9. novembra · Upoznavanje nije prijemni test — CTA: Prijavi dete → Avoid: countdown gimmicks or seat counts. Copy that runs with it: headline "Počinjemo 9. novembra" · primary: Last call text (appendix). |

| B4-2 R7 · Open Day recap Retargeting · from ~27 Oct |  |
| --- | --- |
| INSPIRATION Layout wireframe Reference: Open Day room | NEW · NEEDS PHOTOS PHOTO-BASED · 4:5 + 9:16 Due: 48 h after Igor’s Open Day selects (~Tue 27 Oct) Job: show real kids and parents at NXT — first social proof. Make / improve: • 3-photo collage: one big (a kid presenting / Show & Tell) + two small (hands on a project, parents with the team). • Warm, natural grading; no heavy filters. • Only photos with signed consent; no kids’ names. On the image (exact text): — headline: Ovako je izgledao NXT Open Day. — footer: Upis founding generacije je u toku · CTA: Prijavi dete → Needs: Igor’s Open Day selects + consent list Avoid: posed group photos, photos of kids without consent. Copy that runs with it: headline "Upis prve generacije je u toku" · short "Ovako je izgledao NXT Open Day. Upis founding generacije je u toku — početak 9. novembra." |

| B4-3 Top 2 ads — real-photo versions Prospecting · W4–5 |  |
| --- | --- |
| INSPIRATION Layout idea Reference: curious kid Reference: hands making | NEW · NEEDS PHOTOS PHOTO-BASED · 4:5 + 9:16 Due: Wed 28 Oct Job: does a real photo lift the two best ads? — one change: the visual. Make / improve: • Filip names the top 2 ads on Mon 26 Oct. • Keep text and layout; replace the graphic area with the best matching real photo from the shoot / Open Day. • Kid-eye-height photos, natural light; leave room for the headline. On the image (exact text): — Same text as the original ads. Needs: shoot + Open Day selects Avoid: stock photos, rows of screens, kids without consent. Copy that runs with it: same as the originals. |

| B4-4 Reels — "Kids Explain the Future" + 15 s "scroll → create" Prospecting · W4–5 · video by Igor |  |
| --- | --- |
| INSPIRATION Look for "scroll → create" text cards Reference: scroll b-roll | NEW DESIGN VIDEO 9:16 · design parts Due: Wed 28 Oct (with Igor) Job: two more native Reels from real footage. Make / improve: • Reuse the P6 caption style, end card and cover template. • "Kids Explain the Future": title card with the prompt question. • "Scroll → create": two text cards — cold grey for scrolling, warm brand colours for making. On the image (exact text): — Kids Explain title: Kako zamišljaš školu budućnosti? — scroll → create cards: 4 h dnevno skrolovanja? → Ovde deca stvaraju. → …i predstavljaju šta su napravila. — end card: NXT School · Prijavi dete · početak 9. novembra Needs: Igor’s edits Avoid: music-only reliance — every message must read with sound off. Copy that runs with it: Reel caption adapted (appendix). |