NXT SCHOOL · META LAUNCH · CONTENT REQUESTS

Photos & video: what we have now, what to ask for

Launch ads are designed graphics — no photos needed. Real photos and video then upgrade them week by week. Reference images below are free stock: they show the type of shot, not the final look.

| W1 · LAUNCH Designed statics only | W2 · THIS WEEK Space + team photos | W3 · BEFORE OPEN DAY Shoot photos + first Reel | W4 · AFTER 26 OCT Open Day photos + video |
| --- | --- | --- | --- |

0 STATIC NOW — runs from day 1, zero photos needed Nikola designs these from the brand board

| P1 Hero | P2 Less scrolling | P3 English | P4 AI literacy | P5 / R1 Founding | O1 Open Day | R2 FAQ | R4 Levels |
| --- | --- | --- | --- | --- | --- | --- | --- |

Also design-only: O3 countdown, R6 "Počinjemo 9. novembra". Everything below upgrades or replaces these.

1 PHOTOS NOW — ask Igor this week (a good phone is enough) W2 · within 1–3 days

| The space, empty Ask for: wide shot + corners: tables, materials shelf, presentation zone, entrance. Natural light. No rows of empty computers. Format: photo · horizontal + vertical → Feeds: P1 photo version (W2), R5 background, website | Team portraits Ask for: Mladen, Anita, Ana, Igor, Nikola — chest-up, natural smile, in the space, same light for everyone. Format: photo · leave room to crop 4:5 → Feeds: R5 "Ko stoji iza NXT-a?", website "Ljudi iza NXT-a" | Materials & brand details Ask for: markers, paper, Lego, sketches, posters ("Less scrolling…"), logo, hoodie. Close-ups and top-down. Format: photo · close-up → Feeds: backgrounds for story versions, Open Day ads, social | What this unlocks right away • P1 Hero gets a real space photo instead of the graphic background (W2). • R5 team ad can go live (W3). • Website trust section gets real faces. Plain, real and well-lit beats perfect. Don’t wait for the big shoot. |
| --- | --- | --- | --- |

2 ASK FOR — shoot PHOTOS (Šmiranti kids + 1–2 mentors) W3 · before the Open Day · Igor shoots, Nikola art-directs

| Curious kid, looking up Ask for: age 9–11, looking up / off-frame, space blurred behind, empty area above the head for the headline. Format: photo · vertical + horizontal → Feeds: P1 Hero photo version (W3) | Hands making things Ask for: Lego, paper prototypes, sketches, cardboard — hands only AND hands + face. Format: photo + 5 s clips → Feeds: P2 "Ovo sam danas napravio" (W3), Reel | Kid creating on a screen Ask for: over the shoulder; the screen shows THEIR project (Scratch, Canva, comic). One kid — never rows of screens. Format: photo + short clip → Feeds: P2 / P4 variants, Reel | Pair & team work Ask for: 2–4 kids around one table or laptop — pointing, discussing, laughing. Mixed ages and genders. Format: photo + clip → Feeds: P3 / P4 photo versions, R7 |
| --- | --- | --- | --- |
| Mentor with kids Ask for: mentor at kid eye level, explaining or listening — warm, never lecturing from the front. Format: photo → Feeds: R5 trust, website, landing page | Kid presenting (in English) Ask for: a kid standing, showing a poster or screen; the group listening, then clapping. (Reference shows the composition only.) Format: photo + 10–15 s clip → Feeds: P3 English photo version (W3), Showcase story | Proud moment Ask for: kid holds the finished thing up to the camera — "Ovo sam danas napravio". Format: photo · vertical → Feeds: P2 / Offer variants, "Made at NXT" | Teens as a studio (7–8) Ask for: older kids planning on a whiteboard, laptops, a mic — grown-up, never "kiddy". Format: photo + clip → Feeds: R4 Levels (NXT Lead), Lead-targeted Reels |

3 ASK FOR — VIDEO (same shoot) + OPEN DAY W3 shoot → W4 Open Day, 26 Oct

| "Pitali smo decu…" Ask for: same question to 4–6 kids per age group (1–2 · 3–5 · 6–8): "Kako će izgledati škola za 20 godina?" / "Da li će AI ljude učiniti pametnijim ili lenjim?" Eye level, clip-on mic. Format: 9:16 video → 15–30 s edit → Feeds: P6 Reel (W3) | Scroll → create b-roll Ask for: thumb scrolling a phone (cold, grey) → the same hands drawing or building (warm). 5–10 s each. Format: 9:16 + 4:5 video → Feeds: 15 s Reel "scroll → create" (W4), P2 motion | "Kids Explain the Future" Ask for: one kid explains how they imagine school, jobs or AI in 20–40 s. Prompt them, don’t script them. Format: 9:16 video → Feeds: W4 Reels, organic social | Open Day, 26 Oct Ask for: evening event (18–20 h, bring a light): mini challenge in action, kids’ Show & Tell, parents with the team, one wide room shot, 15–20 s parent quotes ("Šta vam se svidelo?"). Format: photo + video · consent at the door → Feeds: R7 recap, R6, website, January wave |
| --- | --- | --- | --- |

| EVERY SHOT Vertical and horizontal · camera at kid eye level · natural light · creative studio, not a computer classroom · faces happy and busy, not posed. | CONSENT & DELIVERY Signed parental consent for every child · cast kids are never called NXT students · raw files + 20 best selects within 48 h, named by shot (e.g. B6_presenting_01). |
| --- | --- |

Reference photos: Flickr via Openverse, CC BY unless noted — internal reference only, not for ads. Credits: Phil Manker · citirecruitment · Lyn Lomasi · Nisha A · WellspringCS · flickingerbrad · whiteafrican · steveonjava · hackNY (BY-SA) · DFID - UK Department for International Development · greg westfall. · SOZIALHELDEN · NASA Goddard Space Flight Center · EaglebrookSchool.